## Dashboard
July 12-31, 2026 Revenue Sprint - Restrategized
Goal: collect $2,000 by July 31 without betting the whole month on one cold channel.
Metric | Value | How it is calculated / why it matters
Revenue target | 2000 | Cash collected by Jul 31, 2026.
Cash collected |  | Update Daily Metrics every night.
Remaining |  | Amount still required.
Weighted pipeline |  | Amount x probability for active deals.
Replies / conversations |  | Daily market feedback, not vanity outreach.
Calls booked |  | A real buying process starts here.
Proposals sent |  | Formal paid opportunity count.
Paid audits sold |  | Fastest smaller ticket.
Sprint deposits |  | Best path to full $2k.
Task completion |  | Execution check.
Priority | Track | July Role | Reasoning | Offer
1 | Warm network tech/ops gigs | Primary cash path | Highest short-term trust. Use people who know your work to reach founders/operators with manual workflow pain. | $300-$500 audit or $1.5k-$2.5k sprint
2 | Agency/operator automation | Secondary cash path | Agencies understand onboarding/reporting pain and can justify a fixed-scope workflow sprint quickly. | $400 audit or $1.5k-$2k implementation
3 | Western swim/sports academy | Niche beachhead test | Good fit with SwimBuddz proof, but cold trust is slower. Test hard for 5 days before overcommitting. | $300-$500 Lead-to-Enrollment Leak Audit
4 | StrokeLab digital product | Proof and lead magnet | Useful for authority and swim niche credibility, but not the best standalone July cash bet. | Free/low-ticket proof asset
5 | Corporate wellness / local SwimBuddz | Backup channel | Useful where relationships already exist. Do not let it distract from cash conversations. | Corporate intro or cohort conversion
Gate Date | Required Signal | Decision
2026-07-16 | Swim/sports has 5 replies OR 2 calls OR 1 paid-audit interest | If missed, reduce swim cold outreach to 20 percent and shift to warm/agency.
2026-07-20 | At least 1 proposal sent OR $300+ paid audit sold | If missed, make direct high-trust asks and offer smaller paid audit.
2026-07-24 | $500+ collected OR signed sprint/proposal | If missed, stop broad outreach and pursue only strongest 10 leads.
2026-07-28 | $1,000+ collected or committed | Push implementation deposits, urgent audit delivery, and referrals.

## Daily Plan
Day-to-Day Execution Plan: Jul 12-31, 2026
Use Status daily. Apps Script can create reminders from rows where Create Reminder is TRUE.
Date | Day | Start Time | End Time | Track | Priority | Task | Action Steps | Expected Output | Success Metric | Prospect / Asset | Status | Create Reminder | Reminder Lead Mins | Calendar Event ID | Notes
2026-07-12 | Sun | 08:30 | 09:15 | Strategy | P0 | Lock July revenue rule | Write the rule: $2k by Jul 31 from either one implementation sprint or 4-5 paid audits. Confirm the three tracks and the gate dates. | One clear July rule | Rule written and visible on Dashboard | Dashboard | Not Started | TRUE | 15
2026-07-12 | Sun | 11:30 | 13:00 | Pipeline | P0 | Seed 40-prospect universe | Add 10 warm founder/operator contacts, 15 swim/sports academy prospects, 10 agency/operator prospects, and 5 local backup buyers. | 40 pipeline rows | 40 prospects added with pain clues | Pipeline Tracker | Not Started | TRUE | 15
2026-07-12 | Sun | 16:00 | 17:30 | Offers | P0 | Prepare offer assets | Finalize warm ask, swim-school lead-to-enrollment audit, agency onboarding/reporting audit, follow-up, and paid-audit close scripts. | Outreach pack ready | 5 reusable scripts ready | Offers & Templates | Not Started | TRUE | 15
2026-07-12 | Sun | 19:30 | 21:00 | Warm Network | P0 | Send first direct asks | Send 10 warm/referral messages and 5 personalized swim/sports academy messages. Record every send in Pipeline Tracker. | 15 messages sent | 15 logged touches | Warm contacts + swim prospects | Not Started | TRUE | 15
2026-07-12 | Sun | 21:00 | 21:20 | Admin/Review | P0 | Update daily metrics | Record messages sent, replies, calls booked, cash collected, and one market signal. | Day 1 metrics | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-13 | Mon | 07:30 | 08:00 | Admin/Review | P0 | Morning score and reply triage | Check WhatsApp, LinkedIn, email, and calendar. Pick top 10 people to move today. | Priority list | Top 10 next actions selected | Daily Metrics | Not Started | TRUE | 15
2026-07-13 | Mon | 12:30 | 13:15 | Warm Network | P0 | Send 15 warm/referral asks | Ask for one founder/operator intro or one painful workflow worth auditing. Keep it specific and direct. | 15 warm messages | 15 sent and logged | Warm contacts | Not Started | TRUE | 15
2026-07-13 | Mon | 15:30 | 17:00 | Swim/Sports Niche | P0 | Record 2 Loom teardown drafts | Pick 2 swim/sports prospects with visible inquiry/trial/booking leaks. Record short teardown or write detailed notes if Loom is not ready. | 2 teardown assets | 2 personalized observations ready | Swim prospects | Not Started | TRUE | 15
2026-07-13 | Mon | 19:30 | 21:00 | Agency/Operator | P1 | Send 10 agency/operator messages | Target agencies or operators with onboarding, reporting, intake, or dashboard pain. Offer a 48h workflow audit. | 10 messages sent | 10 sent and logged | Agency prospects | Not Started | TRUE | 15
2026-07-14 | Tue | 07:30 | 08:15 | Proof | P0 | Draft SwimBuddz proof one-pager | Summarize SwimBuddz OS, cohort registration, club subscription, payment/referral asks, and workflow complexity as proof of execution. | Proof one-pager draft | One page drafted | SwimBuddz proof | Not Started | TRUE | 15
2026-07-14 | Tue | 12:30 | 13:15 | Warm Network | P0 | Follow up and ask for calls | Follow up all replies and ask for 15-minute calls. Send 10 additional warm asks if reply volume is low. | Calls requested | 3 calls requested/booked | Warm contacts | Not Started | TRUE | 15
2026-07-14 | Tue | 15:30 | 17:30 | Calls/Discovery | P0 | Discovery/call block | Hold booked calls or send call invitations with 2 time windows. Push toward paid audit when pain is concrete. | Calls advanced | 2 calls booked or held | Pipeline Tracker | Not Started | TRUE | 15
2026-07-14 | Tue | 19:30 | 21:00 | Swim/Sports Niche | P0 | Send 12 swim/sports messages | Use the lead-to-enrollment leak angle. Personalize with one clue: trial, assessment, class placement, waitlist, waiver, payment, or follow-up. | 12 niche messages | 12 sent and logged | Swim/sports prospects | Not Started | TRUE | 15
2026-07-15 | Wed | 07:30 | 08:15 | Proof | P0 | Draft tech-gig offer page | Write a one-page offer for AI/backend workflow implementation: problem, deliverables, timeline, price range, proof, and call CTA. | Tech offer page | One offer page drafted | Offer asset | Not Started | TRUE | 15
2026-07-15 | Wed | 12:30 | 13:15 | Warm Network | P0 | Send 15 high-trust touches | Prioritize people who already know your work. Ask for specific intros to founders/operators with messy operations. | 15 touches | 15 sent and logged | Warm contacts | Not Started | TRUE | 15
2026-07-15 | Wed | 15:30 | 17:30 | Calls/Discovery | P0 | Discovery and paid-audit asks | For every serious conversation, ask: what manual workflow costs time or money weekly? Offer the 48h paid audit. | Audit asks | 2 paid-audit asks made | Pipeline Tracker | Not Started | TRUE | 15
2026-07-15 | Wed | 19:30 | 21:00 | Agency/Operator | P1 | Agency workflow audit push | Send 10 agency/operator messages focused on client onboarding, reporting, intake, dashboard, and recurring follow-up workflows. | 10 agency messages | 10 sent and logged | Agency prospects | Not Started | TRUE | 15
2026-07-16 | Thu | 07:30 | 08:15 | Strategy | P0 | Run swim niche gate review | Count swim/sports replies, calls booked, and paid-audit interest. Keep only if there are 5 replies, 2 calls, or 1 paid-audit signal. | Gate decision | Gate marked Hit/Miss | Gate Logic | Not Started | TRUE | 15
2026-07-16 | Thu | 12:30 | 13:15 | Follow-up | P0 | Follow up all non-replies | Send concise follow-up to all prospects touched since Jul 12. Ask a specific yes/no question. | Follow-up wave | 25 follow-ups logged | Pipeline Tracker | Not Started | TRUE | 15
2026-07-16 | Thu | 15:30 | 17:30 | Calls/Discovery | P0 | Convert replies into calls | Push warm and interested cold replies into call slots. Use the paid-audit close script. | Call block filled | 2 calls booked or held | Pipeline Tracker | Not Started | TRUE | 15
2026-07-16 | Thu | 19:30 | 21:00 | Strategy | P0 | Reallocate time based on gate | If swim gate misses, shift 70 percent of time to warm network and agency/operator offers. If it hits, keep swim as 40 percent of outreach. | Time split updated | Next 7 days adjusted | Dashboard | Not Started | TRUE | 15
2026-07-17 | Fri | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-17 | Fri | 12:30 | 13:15 | Warm Network | P0 | Warm direct asks and follow-ups | Send 10-15 warm/referral touches or follow-ups. Ask for a call, a referral, or permission to audit one workflow. | 10-15 warm touches | Touches logged | Warm contacts | Not Started | TRUE | 15
2026-07-17 | Fri | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-17 | Fri | 19:30 | 21:00 | Swim/Sports Niche | P1 | Swim/sports market test outreach | Send 8-12 targeted messages or 2 personalized teardowns. Only continue heavy effort if the Jul 16 gate was hit. | Niche test touches | 8-12 sent or 2 teardowns ready | Swim/sports prospects | Not Started | TRUE | 15
2026-07-17 | Fri | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-18 | Sat | 09:00 | 10:00 | Admin/Review | P0 | Weekend pipeline cleanup | Clean stages, mark dead leads, prioritize top 15, and prepare Monday follow-ups. | Clean pipeline | Top 15 ranked | Pipeline Tracker | Not Started | TRUE | 15
2026-07-18 | Sat | 12:00 | 13:00 | Follow-up | P0 | Weekend follow-ups | Send lighter follow-ups and referral asks. Avoid long cold pitches. | Follow-ups sent | 10 follow-ups logged | Pipeline Tracker | Not Started | TRUE | 15
2026-07-18 | Sat | 16:00 | 17:30 | Proof/Delivery | P1 | Proof asset or paid audit delivery | Create one proof asset, Loom teardown, audit map, or implementation proposal that can be reused. | Reusable asset | 1 asset finished | Proof assets | Not Started | TRUE | 15
2026-07-18 | Sat | 19:30 | 20:30 | Admin/Review | P0 | Weekly scorecard | Score messages, replies, calls, proposals, cash, and next-week allocation. Cut weak channels fast. | Scorecard | Allocation updated | Daily Metrics | Not Started | TRUE | 15
2026-07-19 | Sun | 09:00 | 10:00 | Admin/Review | P0 | Weekend pipeline cleanup | Clean stages, mark dead leads, prioritize top 15, and prepare Monday follow-ups. | Clean pipeline | Top 15 ranked | Pipeline Tracker | Not Started | TRUE | 15
2026-07-19 | Sun | 12:00 | 13:00 | Follow-up | P0 | Weekend follow-ups | Send lighter follow-ups and referral asks. Avoid long cold pitches. | Follow-ups sent | 10 follow-ups logged | Pipeline Tracker | Not Started | TRUE | 15
2026-07-19 | Sun | 16:00 | 17:30 | Proof/Delivery | P1 | Proof asset or paid audit delivery | Create one proof asset, Loom teardown, audit map, or implementation proposal that can be reused. | Reusable asset | 1 asset finished | Proof assets | Not Started | TRUE | 15
2026-07-19 | Sun | 19:30 | 20:30 | Admin/Review | P0 | Weekly scorecard | Score messages, replies, calls, proposals, cash, and next-week allocation. Cut weak channels fast. | Scorecard | Allocation updated | Daily Metrics | Not Started | TRUE | 15
2026-07-20 | Mon | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-20 | Mon | 12:30 | 13:15 | Warm Network | P0 | Warm direct asks and follow-ups | Send 10-15 warm/referral touches or follow-ups. Ask for a call, a referral, or permission to audit one workflow. | 10-15 warm touches | Touches logged | Warm contacts | Not Started | TRUE | 15
2026-07-20 | Mon | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-20 | Mon | 19:30 | 21:00 | Swim/Sports Niche | P1 | Swim/sports market test outreach | Send 8-12 targeted messages or 2 personalized teardowns. Only continue heavy effort if the Jul 16 gate was hit. | Niche test touches | 8-12 sent or 2 teardowns ready | Swim/sports prospects | Not Started | TRUE | 15
2026-07-20 | Mon | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-21 | Tue | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-21 | Tue | 12:30 | 13:15 | Warm Network | P0 | Warm direct asks and follow-ups | Send 10-15 warm/referral touches or follow-ups. Ask for a call, a referral, or permission to audit one workflow. | 10-15 warm touches | Touches logged | Warm contacts | Not Started | TRUE | 15
2026-07-21 | Tue | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-21 | Tue | 19:30 | 21:00 | Agency/Operator | P1 | Agency/operator conversion push | Send targeted audit offers to agencies/operators and use the proof pages to establish credibility quickly. | Agency pipeline advanced | 10 touches or 1 proposal | Agency prospects | Not Started | TRUE | 15
2026-07-21 | Tue | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-22 | Wed | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-22 | Wed | 12:30 | 13:15 | Warm Network | P0 | Warm direct asks and follow-ups | Send 10-15 warm/referral touches or follow-ups. Ask for a call, a referral, or permission to audit one workflow. | 10-15 warm touches | Touches logged | Warm contacts | Not Started | TRUE | 15
2026-07-22 | Wed | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-22 | Wed | 19:30 | 21:00 | Agency/Operator | P1 | Agency/operator conversion push | Send targeted audit offers to agencies/operators and use the proof pages to establish credibility quickly. | Agency pipeline advanced | 10 touches or 1 proposal | Agency prospects | Not Started | TRUE | 15
2026-07-22 | Wed | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-23 | Thu | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-23 | Thu | 12:30 | 13:15 | Warm Network | P0 | Warm direct asks and follow-ups | Send 10-15 warm/referral touches or follow-ups. Ask for a call, a referral, or permission to audit one workflow. | 10-15 warm touches | Touches logged | Warm contacts | Not Started | TRUE | 15
2026-07-23 | Thu | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-23 | Thu | 19:30 | 21:00 | Agency/Operator | P1 | Agency/operator conversion push | Send targeted audit offers to agencies/operators and use the proof pages to establish credibility quickly. | Agency pipeline advanced | 10 touches or 1 proposal | Agency prospects | Not Started | TRUE | 15
2026-07-23 | Thu | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-24 | Fri | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-24 | Fri | 12:30 | 13:15 | Warm Network | P0 | Warm direct asks and follow-ups | Send 10-15 warm/referral touches or follow-ups. Ask for a call, a referral, or permission to audit one workflow. | 10-15 warm touches | Touches logged | Warm contacts | Not Started | TRUE | 15
2026-07-24 | Fri | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-24 | Fri | 19:30 | 21:00 | Agency/Operator | P1 | Agency/operator conversion push | Send targeted audit offers to agencies/operators and use the proof pages to establish credibility quickly. | Agency pipeline advanced | 10 touches or 1 proposal | Agency prospects | Not Started | TRUE | 15
2026-07-24 | Fri | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-25 | Sat | 09:00 | 10:00 | Admin/Review | P0 | Weekend pipeline cleanup | Clean stages, mark dead leads, prioritize top 15, and prepare Monday follow-ups. | Clean pipeline | Top 15 ranked | Pipeline Tracker | Not Started | TRUE | 15
2026-07-25 | Sat | 12:00 | 13:00 | Follow-up | P0 | Weekend follow-ups | Send lighter follow-ups and referral asks. Avoid long cold pitches. | Follow-ups sent | 10 follow-ups logged | Pipeline Tracker | Not Started | TRUE | 15
2026-07-25 | Sat | 16:00 | 17:30 | Proof/Delivery | P1 | Proof asset or paid audit delivery | Create one proof asset, Loom teardown, audit map, or implementation proposal that can be reused. | Reusable asset | 1 asset finished | Proof assets | Not Started | TRUE | 15
2026-07-25 | Sat | 19:30 | 20:30 | Admin/Review | P0 | Weekly scorecard | Score messages, replies, calls, proposals, cash, and next-week allocation. Cut weak channels fast. | Scorecard | Allocation updated | Daily Metrics | Not Started | TRUE | 15
2026-07-26 | Sun | 09:00 | 10:00 | Admin/Review | P0 | Weekend pipeline cleanup | Clean stages, mark dead leads, prioritize top 15, and prepare Monday follow-ups. | Clean pipeline | Top 15 ranked | Pipeline Tracker | Not Started | TRUE | 15
2026-07-26 | Sun | 12:00 | 13:00 | Follow-up | P0 | Weekend follow-ups | Send lighter follow-ups and referral asks. Avoid long cold pitches. | Follow-ups sent | 10 follow-ups logged | Pipeline Tracker | Not Started | TRUE | 15
2026-07-26 | Sun | 16:00 | 17:30 | Proof/Delivery | P1 | Proof asset or paid audit delivery | Create one proof asset, Loom teardown, audit map, or implementation proposal that can be reused. | Reusable asset | 1 asset finished | Proof assets | Not Started | TRUE | 15
2026-07-26 | Sun | 19:30 | 20:30 | Admin/Review | P0 | Weekly scorecard | Score messages, replies, calls, proposals, cash, and next-week allocation. Cut weak channels fast. | Scorecard | Allocation updated | Daily Metrics | Not Started | TRUE | 15
2026-07-27 | Mon | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-27 | Mon | 12:30 | 13:15 | Closing | P0 | Close open proposals | Follow up all open proposals, ask for a decision, and offer a smaller paid audit if a sprint is too large. | Proposal decisions | All open deals touched | Pipeline Tracker | Not Started | TRUE | 15
2026-07-27 | Mon | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-27 | Mon | 19:30 | 21:00 | Delivery/Closing | P0 | Deliver paid audit or final close work | Finish paid audit, send Loom, send implementation plan, or make final decision asks. | Delivery/close output | 1 deliverable or decision ask | Active deals | Not Started | TRUE | 15
2026-07-27 | Mon | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-28 | Tue | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-28 | Tue | 12:30 | 13:15 | Closing | P0 | Close open proposals | Follow up all open proposals, ask for a decision, and offer a smaller paid audit if a sprint is too large. | Proposal decisions | All open deals touched | Pipeline Tracker | Not Started | TRUE | 15
2026-07-28 | Tue | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-28 | Tue | 19:30 | 21:00 | Delivery/Closing | P0 | Deliver paid audit or final close work | Finish paid audit, send Loom, send implementation plan, or make final decision asks. | Delivery/close output | 1 deliverable or decision ask | Active deals | Not Started | TRUE | 15
2026-07-28 | Tue | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-29 | Wed | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-29 | Wed | 12:30 | 13:15 | Closing | P0 | Close open proposals | Follow up all open proposals, ask for a decision, and offer a smaller paid audit if a sprint is too large. | Proposal decisions | All open deals touched | Pipeline Tracker | Not Started | TRUE | 15
2026-07-29 | Wed | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-29 | Wed | 19:30 | 21:00 | Delivery/Closing | P0 | Deliver paid audit or final close work | Finish paid audit, send Loom, send implementation plan, or make final decision asks. | Delivery/close output | 1 deliverable or decision ask | Active deals | Not Started | TRUE | 15
2026-07-29 | Wed | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-30 | Thu | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-30 | Thu | 12:30 | 13:15 | Closing | P0 | Close open proposals | Follow up all open proposals, ask for a decision, and offer a smaller paid audit if a sprint is too large. | Proposal decisions | All open deals touched | Pipeline Tracker | Not Started | TRUE | 15
2026-07-30 | Thu | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-30 | Thu | 19:30 | 21:00 | Delivery/Closing | P0 | Deliver paid audit or final close work | Finish paid audit, send Loom, send implementation plan, or make final decision asks. | Delivery/close output | 1 deliverable or decision ask | Active deals | Not Started | TRUE | 15
2026-07-30 | Thu | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15
2026-07-31 | Fri | 07:30 | 08:00 | Admin/Review | P0 | Morning pipeline review | Review replies, due follow-ups, calls, and yesterday's market signal. Pick the 3 outcomes that matter today. | Daily priority list | 3 outcomes selected | Daily Metrics | Not Started | TRUE | 15
2026-07-31 | Fri | 12:30 | 13:15 | Closing | P0 | Close open proposals | Follow up all open proposals, ask for a decision, and offer a smaller paid audit if a sprint is too large. | Proposal decisions | All open deals touched | Pipeline Tracker | Not Started | TRUE | 15
2026-07-31 | Fri | 15:30 | 17:30 | Calls/Discovery | P0 | Call/proposal block | Hold calls, book calls, or write proposals. Move serious prospects to a paid audit or implementation sprint. | Pipeline advanced | 2 calls/proposals advanced | Pipeline Tracker | Not Started | TRUE | 15
2026-07-31 | Fri | 19:30 | 21:00 | Delivery/Closing | P0 | Deliver paid audit or final close work | Finish paid audit, send Loom, send implementation plan, or make final decision asks. | Delivery/close output | 1 deliverable or decision ask | Active deals | Not Started | TRUE | 15
2026-07-31 | Fri | 21:00 | 21:20 | Admin/Review | P0 | Update metrics and market signal | Record sends, replies, calls, proposals, cash collected, and what the market said back. | Metrics updated | Daily Metrics row updated | Daily Metrics | Not Started | TRUE | 15

## Daily Metrics
Daily Metrics
Answer every night: what did the market say back?
Date | Day | Warm Messages | Swim/Academy Messages | Agency/Operator Messages | Replies | Calls Booked | Calls Held | Proposals Sent | Paid Audits Sold | Sprint Deposits | Cash Collected | Market Signal | Next Adjustment | Done?
2026-07-12 | Sun | [12 empty] | FALSE
2026-07-13 | Mon | [12 empty] | FALSE
2026-07-14 | Tue | [12 empty] | FALSE
2026-07-15 | Wed | [12 empty] | FALSE
2026-07-16 | Thu | [12 empty] | FALSE
2026-07-17 | Fri | [12 empty] | FALSE
2026-07-18 | Sat | [12 empty] | FALSE
2026-07-19 | Sun | [12 empty] | FALSE
2026-07-20 | Mon | [12 empty] | FALSE
2026-07-21 | Tue | [12 empty] | FALSE
2026-07-22 | Wed | [12 empty] | FALSE
2026-07-23 | Thu | [12 empty] | FALSE
2026-07-24 | Fri | [12 empty] | FALSE
2026-07-25 | Sat | [12 empty] | FALSE
2026-07-26 | Sun | [12 empty] | FALSE
2026-07-27 | Mon | [12 empty] | FALSE
2026-07-28 | Tue | [12 empty] | FALSE
2026-07-29 | Wed | [12 empty] | FALSE
2026-07-30 | Thu | [12 empty] | FALSE
2026-07-31 | Fri | [12 empty] | FALSE

## Pipeline Tracker
Pipeline Tracker
Do not count outreach as progress until it creates replies, calls, proposals, cash, or useful market feedback.
Date Added | Track | Segment | Market | Prospect | Contact | URL / LinkedIn | Pain Clue | Current Tools | Offer | Stage | Amount | Probability | Weighted Value | Next Action | Next Action Date | Last Touch | Notes
2026-07-12 | Warm Network | Founder/operator contact | Your network | Warm Contact 1 |  |  | Knows your work or can intro you to founders/operators. |  | Referral Ask | Not Contacted | 0 | 0.2 |  | Replace with actual name and send direct ask. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Former colleague/client | Your network | Warm Contact 2 |  |  | Has seen your technical ability or execution. |  | Referral Ask | Not Contacted | 0 | 0.2 |  | Replace with actual name and send direct ask. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Founder friend | Your network | Warm Contact 3 |  |  | Can name one founder/operator with manual workflow pain. |  | Referral Ask | Not Contacted | 0 | 0.2 |  | Replace with actual name and send direct ask. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | SwimBuddz member/contact | Your network | Warm Contact 4 |  |  | Trust path through SwimBuddz/community. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Open-source/tech contact | Your network | Warm Contact 5 |  |  | Can refer agency/founder/operator contacts. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Previous school/Unilag contact | Your network | Warm Contact 6 |  |  | AI/ML credibility path. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Rolf/expert path | Your network | Warm Contact 7 |  |  | Can advise or introduce higher-quality buyers. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Community founder | Your network | Warm Contact 8 |  |  | Likely knows people running small operations. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Past project stakeholder | Your network | Warm Contact 9 |  |  | Can validate backend/automation execution. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Warm Network | Trusted friend with founder network | Your network | Warm Contact 10 |  |  | Can connect you quickly without cold trust problem. |  | Referral Ask | Not Contacted | 0 | 0.15 |  | Replace with actual name and ask for intro. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | Goldfish Swim School |  | https://goldfishswimschool.com/ | Assessment, registration portal, class levels, multiple locations, make-up lessons. |  | Paid Audit | Not Contacted | 400 | 0.1 |  | Target a local franchise owner/operator, not only HQ. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | British Swim School |  | https://britishswimschool.com/ | Location finder, swim assessment, programs for children/adults/adaptive aquatics. |  | Paid Audit | Not Contacted | 400 | 0.1 |  | Target a local owner/operator. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | Aqua-Tots Swim Schools |  | https://www.aqua-tots.com/ | Enrollment, levels, franchise locations, likely parent follow-up workflow. |  | Paid Audit | Not Contacted | 400 | 0.1 |  | Target regional/franchise operator. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | SafeSplash Swim School |  | https://www.safesplash.com/ | Kids/adult lessons, locations, booking/enrollment flow. |  | Paid Audit | Not Contacted | 400 | 0.1 |  | Target location-level operator. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | Big Blue Swim School |  | https://bigblueswimschool.com/ | Class enrollment, parent-facing scheduling, multi-location operation. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Likely has mature systems; use as research or local franchise target. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | Emler Swim School |  | https://emlerswimschool.com/ | Class levels, enrollment, parent/student progression. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Look for individual location decision maker. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | Foss Swim School |  | https://www.fossswimschool.com/ | Enrollment, class levels, multi-location operations. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Research local operator before messaging. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | US | Bear Paddle Swim School |  | https://bearpaddle.com/ | Lesson enrollment and progression flow. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Research local/franchise contact. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Private swim lessons | US/Canada | Sunsational Swim School |  | https://www.sunsationalswimschool.com/ | Private lesson inquiry, matching, scheduling, instructor/customer coordination. |  | Paid Audit | Not Contacted | 400 | 0.1 |  | Lead matching workflow may be a strong angle. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Private swim lessons | US/Canada | AquaMobile Swim School |  | https://aquamobileswim.com/ | At-home lesson booking, instructor matching, payment/follow-up flow. |  | Paid Audit | Not Contacted | 400 | 0.1 |  | Lead-to-instructor matching workflow may be relevant. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim analysis/coaching | US | SwimLabs |  | https://www.swimlabs.com/ | Video analysis, lessons, locations, assessment/booking workflow. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Good StrokeLab proof comparison. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | Australia | Carlile Swimming |  | https://www.carlile.com.au/ | Learn-to-swim program, levels, enrollment, multiple centers. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | May be too mature; use as research or local contact. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | Australia | State Swim |  | https://www.stateswim.com.au/ | Class levels, booking/enrollment, multiple locations. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Research franchise/location operators. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | Australia | JUMP! Swim Schools |  | https://jumpswimschools.com.au/ | Small-class swim school model, franchise locations, enrollment flow. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Target local operator if contact is visible. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Swim/Sports Niche | Swim school | Australia | Kingswim |  | https://www.kingswim.com.au/ | Lessons, class levels, customer booking, multi-location operations. |  | Paid Audit | Not Contacted | 400 | 0.08 |  | Research individual center operators. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | B2B SaaS agency | US/Canada | Powered by Search |  | https://www.poweredbysearch.com/ | Client onboarding, reporting, campaign dashboards, recurring delivery process. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | Target ops/delivery leader, not generic contact. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Inbound agency | US | SmartBug Media |  | https://www.smartbugmedia.com/ | Client reporting, onboarding, HubSpot/RevOps workflows. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | May already be mature; use specific workflow angle. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Performance agency | US | KlientBoost |  | https://klientboost.com/ | Client reporting and recurring performance communication. |  | Implementation Sprint | Not Contacted | 1800 | 0.07 |  | Likely mature; prioritize if you can find ops pain. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | SaaS marketing agency | US/UK | Directive Consulting |  | https://directiveconsulting.com/ | SaaS client onboarding, reporting, dashboards. |  | Implementation Sprint | Not Contacted | 1800 | 0.07 |  | Likely mature; use as research if no contact path. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Content agency | US | Siege Media |  | https://www.siegemedia.com/ | Content production workflow, client approvals, reporting. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | Workflow operations may be more relevant than AI pitch. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | SEO agency | US | SimpleTiger |  | https://www.simpletiger.com/ | SEO deliverables, reporting, recurring client workflows. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | Look for founder/ops contact. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Growth agency | US | NoGood |  | https://nogood.io/ | Growth experiments, reporting, internal workflow handoffs. |  | Implementation Sprint | Not Contacted | 1800 | 0.07 |  | May be too sophisticated; use if specific pain clue exists. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Growth agency | US | Tuff Growth |  | https://tuffgrowth.com/ | Client onboarding/reporting and marketing ops workflows. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | Find founder/ops contact. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Content agency | US | Grow and Convert |  | https://www.growandconvert.com/ | Content workflow, research, client reporting, handoff process. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | Specific workflow observation needed. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Agency/Operator | Content agency | US | Codeless |  | https://getcodeless.com/ | Content operations, approvals, recurring reporting. |  | Implementation Sprint | Not Contacted | 1800 | 0.08 |  | Specific workflow observation needed. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Corporate Wellness | Fintech/company | Nigeria | Flutterwave |  | https://flutterwave.com/ | Corporate wellness/community angle; only pursue through warm intro. |  | Corporate Intro | Not Contacted | 500 | 0.05 |  | Do not cold pitch HR first; find warm path. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Corporate Wellness | Fintech/company | Nigeria | Paystack |  | https://paystack.com/ | Corporate wellness/community angle; only pursue through warm intro. |  | Corporate Intro | Not Contacted | 500 | 0.05 |  | Do not cold pitch HR first; find warm path. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Corporate Wellness | Fintech/company | Nigeria | PiggyVest |  | https://www.piggyvest.com/ | Corporate wellness/community angle; only pursue through warm intro. |  | Corporate Intro | Not Contacted | 500 | 0.05 |  | Do not cold pitch HR first; find warm path. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Corporate Wellness | Tech talent/company | Remote/Africa | Andela |  | https://andela.com/ | Wellness/community/team-building angle; only pursue through warm intro. |  | Corporate Intro | Not Contacted | 500 | 0.05 |  | Find people/ops contact through network. | 2026-07-12 |  | Starter seed. Verify contact before sending.
2026-07-12 | Corporate Wellness | Fintech/company | Nigeria | Cowrywise |  | https://cowrywise.com/ | Corporate wellness/community angle; only pursue through warm intro. |  | Corporate Intro | Not Contacted | 500 | 0.05 |  | Find warm intro first. | 2026-07-12 |  | Starter seed. Verify contact before sending.

## Starter Prospects
Starter 40 Prospects / Slots
Replace the 10 warm placeholders with real people. Public cold prospects still need owner/operator contact research before messaging.
Track | Segment | Market | Prospect | Contact | URL / LinkedIn | Pain Clue | Offer | Amount | Probability | Next Action | Stage
Warm Network | Founder/operator contact | Your network | Warm Contact 1 |  |  | Knows your work or can intro you to founders/operators. | Referral Ask | 0 | 0.2 | Replace with actual name and send direct ask. | Not Contacted
Warm Network | Former colleague/client | Your network | Warm Contact 2 |  |  | Has seen your technical ability or execution. | Referral Ask | 0 | 0.2 | Replace with actual name and send direct ask. | Not Contacted
Warm Network | Founder friend | Your network | Warm Contact 3 |  |  | Can name one founder/operator with manual workflow pain. | Referral Ask | 0 | 0.2 | Replace with actual name and send direct ask. | Not Contacted
Warm Network | SwimBuddz member/contact | Your network | Warm Contact 4 |  |  | Trust path through SwimBuddz/community. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Warm Network | Open-source/tech contact | Your network | Warm Contact 5 |  |  | Can refer agency/founder/operator contacts. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Warm Network | Previous school/Unilag contact | Your network | Warm Contact 6 |  |  | AI/ML credibility path. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Warm Network | Rolf/expert path | Your network | Warm Contact 7 |  |  | Can advise or introduce higher-quality buyers. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Warm Network | Community founder | Your network | Warm Contact 8 |  |  | Likely knows people running small operations. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Warm Network | Past project stakeholder | Your network | Warm Contact 9 |  |  | Can validate backend/automation execution. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Warm Network | Trusted friend with founder network | Your network | Warm Contact 10 |  |  | Can connect you quickly without cold trust problem. | Referral Ask | 0 | 0.15 | Replace with actual name and ask for intro. | Not Contacted
Swim/Sports Niche | Swim school | US | Goldfish Swim School |  | https://goldfishswimschool.com/ | Assessment, registration portal, class levels, multiple locations, make-up lessons. | Paid Audit | 400 | 0.1 | Target a local franchise owner/operator, not only HQ. | Not Contacted
Swim/Sports Niche | Swim school | US | British Swim School |  | https://britishswimschool.com/ | Location finder, swim assessment, programs for children/adults/adaptive aquatics. | Paid Audit | 400 | 0.1 | Target a local owner/operator. | Not Contacted
Swim/Sports Niche | Swim school | US | Aqua-Tots Swim Schools |  | https://www.aqua-tots.com/ | Enrollment, levels, franchise locations, likely parent follow-up workflow. | Paid Audit | 400 | 0.1 | Target regional/franchise operator. | Not Contacted
Swim/Sports Niche | Swim school | US | SafeSplash Swim School |  | https://www.safesplash.com/ | Kids/adult lessons, locations, booking/enrollment flow. | Paid Audit | 400 | 0.1 | Target location-level operator. | Not Contacted
Swim/Sports Niche | Swim school | US | Big Blue Swim School |  | https://bigblueswimschool.com/ | Class enrollment, parent-facing scheduling, multi-location operation. | Paid Audit | 400 | 0.08 | Likely has mature systems; use as research or local franchise target. | Not Contacted
Swim/Sports Niche | Swim school | US | Emler Swim School |  | https://emlerswimschool.com/ | Class levels, enrollment, parent/student progression. | Paid Audit | 400 | 0.08 | Look for individual location decision maker. | Not Contacted
Swim/Sports Niche | Swim school | US | Foss Swim School |  | https://www.fossswimschool.com/ | Enrollment, class levels, multi-location operations. | Paid Audit | 400 | 0.08 | Research local operator before messaging. | Not Contacted
Swim/Sports Niche | Swim school | US | Bear Paddle Swim School |  | https://bearpaddle.com/ | Lesson enrollment and progression flow. | Paid Audit | 400 | 0.08 | Research local/franchise contact. | Not Contacted
Swim/Sports Niche | Private swim lessons | US/Canada | Sunsational Swim School |  | https://www.sunsationalswimschool.com/ | Private lesson inquiry, matching, scheduling, instructor/customer coordination. | Paid Audit | 400 | 0.1 | Lead matching workflow may be a strong angle. | Not Contacted
Swim/Sports Niche | Private swim lessons | US/Canada | AquaMobile Swim School |  | https://aquamobileswim.com/ | At-home lesson booking, instructor matching, payment/follow-up flow. | Paid Audit | 400 | 0.1 | Lead-to-instructor matching workflow may be relevant. | Not Contacted
Swim/Sports Niche | Swim analysis/coaching | US | SwimLabs |  | https://www.swimlabs.com/ | Video analysis, lessons, locations, assessment/booking workflow. | Paid Audit | 400 | 0.08 | Good StrokeLab proof comparison. | Not Contacted
Swim/Sports Niche | Swim school | Australia | Carlile Swimming |  | https://www.carlile.com.au/ | Learn-to-swim program, levels, enrollment, multiple centers. | Paid Audit | 400 | 0.08 | May be too mature; use as research or local contact. | Not Contacted
Swim/Sports Niche | Swim school | Australia | State Swim |  | https://www.stateswim.com.au/ | Class levels, booking/enrollment, multiple locations. | Paid Audit | 400 | 0.08 | Research franchise/location operators. | Not Contacted
Swim/Sports Niche | Swim school | Australia | JUMP! Swim Schools |  | https://jumpswimschools.com.au/ | Small-class swim school model, franchise locations, enrollment flow. | Paid Audit | 400 | 0.08 | Target local operator if contact is visible. | Not Contacted
Swim/Sports Niche | Swim school | Australia | Kingswim |  | https://www.kingswim.com.au/ | Lessons, class levels, customer booking, multi-location operations. | Paid Audit | 400 | 0.08 | Research individual center operators. | Not Contacted
Agency/Operator | B2B SaaS agency | US/Canada | Powered by Search |  | https://www.poweredbysearch.com/ | Client onboarding, reporting, campaign dashboards, recurring delivery process. | Implementation Sprint | 1800 | 0.08 | Target ops/delivery leader, not generic contact. | Not Contacted
Agency/Operator | Inbound agency | US | SmartBug Media |  | https://www.smartbugmedia.com/ | Client reporting, onboarding, HubSpot/RevOps workflows. | Implementation Sprint | 1800 | 0.08 | May already be mature; use specific workflow angle. | Not Contacted
Agency/Operator | Performance agency | US | KlientBoost |  | https://klientboost.com/ | Client reporting and recurring performance communication. | Implementation Sprint | 1800 | 0.07 | Likely mature; prioritize if you can find ops pain. | Not Contacted
Agency/Operator | SaaS marketing agency | US/UK | Directive Consulting |  | https://directiveconsulting.com/ | SaaS client onboarding, reporting, dashboards. | Implementation Sprint | 1800 | 0.07 | Likely mature; use as research if no contact path. | Not Contacted
Agency/Operator | Content agency | US | Siege Media |  | https://www.siegemedia.com/ | Content production workflow, client approvals, reporting. | Implementation Sprint | 1800 | 0.08 | Workflow operations may be more relevant than AI pitch. | Not Contacted
Agency/Operator | SEO agency | US | SimpleTiger |  | https://www.simpletiger.com/ | SEO deliverables, reporting, recurring client workflows. | Implementation Sprint | 1800 | 0.08 | Look for founder/ops contact. | Not Contacted
Agency/Operator | Growth agency | US | NoGood |  | https://nogood.io/ | Growth experiments, reporting, internal workflow handoffs. | Implementation Sprint | 1800 | 0.07 | May be too sophisticated; use if specific pain clue exists. | Not Contacted
Agency/Operator | Growth agency | US | Tuff Growth |  | https://tuffgrowth.com/ | Client onboarding/reporting and marketing ops workflows. | Implementation Sprint | 1800 | 0.08 | Find founder/ops contact. | Not Contacted
Agency/Operator | Content agency | US | Grow and Convert |  | https://www.growandconvert.com/ | Content workflow, research, client reporting, handoff process. | Implementation Sprint | 1800 | 0.08 | Specific workflow observation needed. | Not Contacted
Agency/Operator | Content agency | US | Codeless |  | https://getcodeless.com/ | Content operations, approvals, recurring reporting. | Implementation Sprint | 1800 | 0.08 | Specific workflow observation needed. | Not Contacted
Corporate Wellness | Fintech/company | Nigeria | Flutterwave |  | https://flutterwave.com/ | Corporate wellness/community angle; only pursue through warm intro. | Corporate Intro | 500 | 0.05 | Do not cold pitch HR first; find warm path. | Not Contacted
Corporate Wellness | Fintech/company | Nigeria | Paystack |  | https://paystack.com/ | Corporate wellness/community angle; only pursue through warm intro. | Corporate Intro | 500 | 0.05 | Do not cold pitch HR first; find warm path. | Not Contacted
Corporate Wellness | Fintech/company | Nigeria | PiggyVest |  | https://www.piggyvest.com/ | Corporate wellness/community angle; only pursue through warm intro. | Corporate Intro | 500 | 0.05 | Do not cold pitch HR first; find warm path. | Not Contacted
Corporate Wellness | Tech talent/company | Remote/Africa | Andela |  | https://andela.com/ | Wellness/community/team-building angle; only pursue through warm intro. | Corporate Intro | 500 | 0.05 | Find people/ops contact through network. | Not Contacted
Corporate Wellness | Fintech/company | Nigeria | Cowrywise |  | https://cowrywise.com/ | Corporate wellness/community angle; only pursue through warm intro. | Corporate Intro | 500 | 0.05 | Find warm intro first. | Not Contacted

## Prospect Criteria
Prospect Criteria
Use this to decide who belongs in the first 40 prospects.
Quota | Segment | Ideal Buyer | Pain Clues | Where To Find | First Offer | Disqualifiers | July Priority
10 | Warm founder/operator contacts | People who already know your ability or can introduce you to operators. | Manual admin, missed follow-ups, data scattered across tools, repeated reporting. | LinkedIn, WhatsApp, former projects, founders in your circle. | Referral ask or paid workflow audit. | No trust path, no operational pain, no budget owner. | Highest
15 | Western swim schools / sports academies | Owners or operators of swim schools, adult swim programs, triathlon swim coaches, kids sports academies. | Inquiry form, trial/assessment booking, class levels, waitlist, waivers, multiple locations, payment follow-up. | USA Swimming, USMS, Google Maps, local directories, LinkedIn. | Lead-to-Enrollment Leak Audit. | No clear owner/contact, no booking/enrollment flow, tiny volunteer-only club. | Market test
10 | Agencies / small operators | Small agencies, implementation shops, consultants, SaaS operators, or service teams. | Client onboarding, intake docs, reporting, dashboards, recurring status updates, messy handoff. | LinkedIn, founder communities, agency directories, warm intros. | Client Onboarding/Reporting Workflow Audit. | Pure content agencies with no ops pain, no decision maker, no budget. | High
5 | Backup local/corporate SwimBuddz | HR/People/Ops teams, community leaders, wellness decision makers, clubs. | Employee wellness, beginner adult swimming, safety, community, team bonding. | Warm network, LinkedIn, local companies, past SwimBuddz contacts. | Corporate swim/wellness intro call. | No warm path, no wellness budget, long procurement. | Backup

## Offers & Templates
Offers & Templates
Use direct, concrete offers. Do not sell generic AI automation.
Track | Asset | Copy / Script | Use When | Notes
Strategy | July rule | By July 31, collect $2k from either one $1.5k-$2.5k implementation sprint or 4-5 $300-$500 paid audits. Primary cash path is warm-network tech/ops gigs. Swim/sports academy is a 5-day niche test, not the only bet. | Dashboard / daily reminder | This prevents overcommitting to a slow cold market.
Warm Network | Direct ask | Hey [Name], quick ask. I am looking to close 1-2 fixed-scope workflow automation projects before July 31. I am strongest at AI/backend systems, integrations, internal tools, dashboards, and operational workflows. Do you know any founder/operator losing time or leads because a manual process is messy? I can do either a 48h paid audit or a 10-day implementation sprint. | People who know your work | Highest short-term probability because trust already exists.
Swim/Sports Niche | Cold opener | Hi [Name], I run SwimBuddz and noticed [specific clue from their booking/enrollment flow]. A lot of swim schools lose leads between inquiry, assessment, trial, class placement, payment, and follow-up. I am testing a 48h Lead-to-Enrollment Leak Audit: Loom teardown, flow map, quick fixes, and an implementation plan. Would it be useful if I sent one specific observation from your current flow? | Owners/operators with visible lead flow | Ask permission first if there is no warm connection.
Agency/Operator | Cold opener | Hi [Name], I noticed your team handles [client/service type]. Agencies often lose time in client onboarding and reporting: intake docs, status updates, dashboards, recurring reports, and follow-ups. I build fixed-scope backend/automation workflows. Open to me sending one specific observation about a workflow you could tighten? | Small agencies/operators | This is the fastest adjacent niche if swim replies are weak.
Closing | Paid audit close | Based on what you described, I would not start with a full build. I would do a 48h workflow audit first: map the current flow, identify leaks, propose quick wins, and give you the implementation plan. It is $400 and I credit it toward the sprint if we build. Want me to do that this week? | After a call or strong reply | Do not leave conversations at 'let me know'.
Closing | Sprint close | The sprint would focus on one workflow end-to-end: [workflow]. Deliverables: intake/booking flow, integrations, reminders, payment/status tracking, simple dashboard, error handling, and handover notes. Timeline: 10 business days. Price: $1.5k-$2.5k depending on scope. To reserve the week, I take a 50 percent deposit. | When audit/call reveals concrete pain | Keep scope narrow; one workflow only.
Follow-up | Follow-up 1 | Quick follow-up on this. Is lead follow-up / onboarding / reporting currently a real problem for you, or is it already handled well enough? | 2 days after no reply | Forces useful market feedback.
Follow-up | Referral follow-up | No worries if not you. Is there one founder/operator you think this would be more relevant for? | Warm network non-buyer | Converts non-buyers into intros.

## Gate Logic
Gate Logic
Use the market response to decide. Do not argue with weak signals.
Date | Question | Green Signal | Red Signal | Action If Green | Action If Red
2026-07-16 | Is swim/sports academy a real July cash path? | 5 replies, 2 calls, or 1 paid-audit interest. | Fewer than 3 replies and no call momentum. | Keep swim at 40 percent of outreach and continue Loom teardowns. | Reduce swim to 20 percent; shift to warm network and agency/operator.
2026-07-20 | Is any channel producing buyer conversations? | 1 proposal or $300+ paid audit sold. | Only polite replies and no paid ask accepted. | Push proposals and sprint deposits. | Make direct high-trust asks; lower friction with $300 audit.
2026-07-24 | Is cash collection on track? | $500+ collected or signed sprint. | No committed money. | Deliver fast and ask for referrals/deposit. | Stop cold experiments; work only strongest 10 leads.
2026-07-28 | Can $2k close by Jul 31? | $1k+ collected/committed and at least one sprint in negotiation. | No committed buyer. | Push sprint deposit and paid audit bundle. | Use immediate cash alternatives: direct contract work, referrals, local corporate intro.

## Reminder Config
Reminder Config
Paste Apps Script Code into Extensions > Apps Script, then run syncPlanReminders.
Key | Value | Description
Calendar ID | primary | Use primary calendar unless you paste a specific calendar ID.
Event Prefix | Revenue Sprint | Prefix added to calendar events.
Max Events Per Run | 20 | Keeps Apps Script under event creation limits. Run again later for remaining rows.
Dry Run | FALSE | Set TRUE to test logging without creating events.
Timezone | Africa/Lagos | Your local planning timezone.
Start Date | 2026-07-12 | First date in this workbook.
End Date | 2026-07-31 | Last date in this workbook.

## Apps Script Code
Apps Script Code
Copy the code below into Apps Script for idempotent calendar reminders.
const PLAN_SHEET_NAME = 'Daily Plan'; const CONFIG_SHEET_NAME = 'Reminder Config'; function syncPlanReminders() { const ss = SpreadsheetApp.getActive(); const plan = ss.getSheetByName(PLAN_SHEET_NAME); const config = readConfig_(); const calendar = getCalendar_(config); const maxEvents = Number(config['Max Events Per Run'] ¦¦ 20); const dryRun = String(config['Dry Run'] ¦¦ 'FALSE').toUpperCase() === 'TRUE'; const prefix = config['Event Prefix'] ¦¦ 'Revenue Sprint'; const values = plan.getDataRange().getValues(); const h = headerMap_(values[3]); let changed = 0; for (let r = 4; r < values.length; r++) { if (changed >= maxEvents) break; const row = values[r]; if (!row[h['Date']] ¦¦ String(row[h['Create Reminder']]).toUpperCase() !== 'TRUE') continue; const status = String(row[h['Status']] ¦¦ '').trim(); if (['Done', 'Skipped'].includes(status)) continue; const start = parseTime_(row[h['Date']], row[h['Start Time']]); const end = parseTime_(row[h['Date']], row[h['End Time']]); if (!start ¦¦ !end ¦¦ end <= start) continue; const title = `${prefix}: ${row[h['Task']]}`; const description = eventDescription_(row, h); const eventIdCol = h['Calendar Event ID'] + 1; let eventId = row[h['Calendar Event ID']]; let event = eventId ? calendar.getEventById(eventId) : null; if (dryRun) { Logger.log(`[DRY RUN] ${title} ${start} - ${end}`); continue; } if (event) { event.setTitle(title); event.setTime(start, end); event.setDescription(description); resetReminder_(event, row[h['Reminder Lead Mins']]); } else { event = calendar.createEvent(title, start, end, { description }); resetReminder_(event, row[h['Reminder Lead Mins']]); plan.getRange(r + 1, eventIdCol).setValue(event.getId()); } changed++; Utilities.sleep(250); } Logger.log(`Processed ${changed} reminders. If you need more, run syncPlanReminders again after a few minutes.`); } function clearCalendarEventIdsOnly() { const ss = SpreadsheetApp.getActive(); const plan = ss.getSheetByName(PLAN_SHEET_NAME); const values = plan.getDataRange().getValues(); const h = headerMap_(values[3]); plan.getRange(5, h['Calendar Event ID'] + 1, values.length - 4, 1).clearContent(); } function readConfig_() { const sheet = SpreadsheetApp.getActive().getSheetByName(CONFIG_SHEET_NAME); const rows = sheet.getDataRange().getValues(); const config = {}; rows.forEach(row => { if (row[0]) config[String(row[0]).trim()] = row[1]; }); return config; } function getCalendar_(config) { const id = config['Calendar ID']; if (id && id !== 'primary') return CalendarApp.getCalendarById(id); return CalendarApp.getDefaultCalendar(); } function headerMap_(headerRow) { const h = {}; headerRow.forEach((name, idx) => { if (name) h[String(name).trim()] = idx; }); return h; } function parseTime_(dateValue, timeText) { const d = new Date(dateValue); const parts = String(timeText).trim().split(':').map(Number); d.setHours(parts[0] ¦¦ 0, parts[1] ¦¦ 0, 0, 0); return d; } function eventDescription_(row, h) { return [ `Track: ${row[h['Track']]}`, `Priority: ${row[h['Priority']]}`, '', 'Action steps:', row[h['Action Steps']], '', `Expected output: ${row[h['Expected Output']]}`, `Success metric: ${row[h['Success Metric']]}`, `Asset/prospect: ${row[h['Prospect / Asset']]}`, '', `Sheet status: ${row[h['Status']]}` ].join('\n'); } function resetReminder_(event, leadMins) { event.removeAllReminders(); const mins = Number(leadMins ¦¦ 15); event.addPopupReminder(mins); }

## Source Notes
Source Notes
Research basis for the strategy. These links should be rechecked before a larger campaign.
Source | Link | What It Supports | Planning Implication | Reliability
USA Swimming | https://www.usaswimming.org/find-a-team | Large organized swim team ecosystem and directories. | There are many swim-related organizations to target, but club/team is not the same as paid school/operator. | Official
U.S. Masters Swimming | https://www.usms.org/clubs | Adult swim club/program ecosystem. | Adult swim and triathlon-related programs are a relevant adjacent audience. | Official
Jackrabbit Class | https://www.jackrabbitclass.com/ | Youth activity businesses already buy registration, scheduling, enrollment, billing, and engagement software. | Customers pay for operations tools, but there are strong incumbents. Sell implementation around the current stack, not a generic OS. | Vendor
iClassPro | https://www.iclasspro.com/ | Class/camp registration, payments, customer portal, and activity-center management. | Competition is real. The wedge must be a specific leak audit and implementation, not 'software for swim schools'. | Vendor
Uplifter | https://www.uplifterinc.com/ | Sports/activity software for registration, payments, waitlists, communications, forms, and reporting. | Lead-to-enrollment and admin workflows are real pains, but many buyers already have a platform. | Vendor
Amilia | https://www.amilia.com/ | Recreation/YMCA software positioning around registration, membership, operations, and admin time savings. | Operational time savings and enrollment capacity are business outcomes buyers understand. | Vendor
AgencyAnalytics | https://agencyanalytics.com/ | Agencies buy reporting/dashboard automation. | Agency onboarding/reporting is a credible adjacent niche and may close faster than cold swim schools. | Vendor

## Lookups
Lookups
Dropdown source values.
Statuses | Tracks | Stages | Priorities | Offers
Not Started | Warm Network | Not Contacted | P0 | Paid Audit
In Progress | Agency/Operator | Messaged | P1 | Implementation Sprint
Waiting | Swim/Sports Niche | Replied | P2 | Referral Ask
Done | Corporate Wellness | Call Booked |  | Corporate Intro
Skipped | StrokeLab | Call Held |  | Digital Product
| Admin/Review | Proposal Sent |  | Other
| Strategy | Paid Audit
| Proof | Sprint Won
| Closing | Lost
| Delivery/Closing | Nurture
Other