## Launch Phase (30 Days)
Day | Phase | Platform | Content / Action | Distribution | Notes
-7 to -1 | Pre-Launch | — | Create IG + TikTok accounts (Business). Set up Linktree. Prep 6-9 posts. Brief coaches with filming briefs. | Send WA message: "Socials launching next week — follow us on day 1!" | Don't announce handles yet
1 | Soft Launch | IG + TT | Post 3 strongest pieces: 1 transformation carousel, 1 community reel, 1 coach tip | — (no announcement yet) | Building grid before anyone sees it
2 | Soft Launch | IG + TT | Post 2 more: 1 testimonial graphic, 1 stat card post | Start populating IG Highlights with Stories | Grid now has 5 posts
3 | Soft Launch | IG + TT | Post 1-2 more: behind-the-scenes or member spotlight | — | Grid: 6-8 posts. Profile looks established.
4 | HARD LAUNCH | All | Post your best piece of content — the one most likely to get engagement | WhatsApp announcement (see Playbook Ch.7). DM top 10 members individually. Coaches post Stories tagging @swimbuddz. Website banner. | THIS IS THE BIG DAY. All hands on deck for engagement.
5-7 | Launch Week | IG + TT | Post daily or every other day. Use pre-made content backlog. Mix pillars. | Share each post to WA within 30 min. Reply to ALL comments within 1 hour. | Algorithm is evaluating your new account aggressively
8-14 | Growth | IG + TT | 2x/week posting. Start Founding 50 campaign. 1 member feature + 1 other pillar. | DM featured members to reshare. Engage with 5 Lagos fitness/lifestyle accounts daily (genuine comments). | Founding 50 builds grid + social proof fast
15-21 | Settling | IG + TT | Transition to 1x/week. First WhatsApp repurpose (QOTW carousel). Film first video testimonial (Uche, Onyinye, or Esther). | Continue WA seeding. Start tracking DM enquiries. | The sustainable cadence begins here
22-30 | Review | IG + TT | 1x/week posting per Content Calendar. Review metrics. | Pull IG Insights: saves, shares, profile visits, website clicks. Count DMs. Identify top-performing content type. | Adjust Month 2 calendar based on data

## Launch Phase
Phase | Date | Pillar | Action | Instagram | TikTok | Distribution Plan | Goal
Pre-Launch Week -2 |  | Launch | Set up accounts + Linktree | Create Business account @swimbuddz Bio: "the global swimming community starting in Lagos. Learn. Train. Belong. 🏊" Profile photo: logo Set up Highlights (empty for now) | Create Business account @swimbuddz Bio: "the global swimming community starting in Lagos 🏊 Watch adults learn to swim" Profile photo: same logo | Internal only. Don't announce yet. | Accounts live and configured
Pre-Launch Week -2 |  | Launch | Set up Linktree + landing page | Bio link → Linktree URL | Bio link → same Linktree URL | Test all links work. Share internally for QA. | Conversion path ready
Pre-Launch Week -1 |  | Launch | Seed content (Post 1 of 4) Before public announcement | Carousel: "Who is SwimBuddz?" — 5 slides explaining Community, Club, Academy with pool photos | 30s: "the global swimming community starting in Lagos" montage of best pool footage | DO NOT announce yet. Just post silently. | Profile doesn't look empty when people arrive
Pre-Launch Week -1 |  | Launch | Seed content (Post 2 of 4) | Reel: Best session moments compilation (30-45s) | Same reel, slightly re-edited for TikTok | Still silent. No announcement. | 2 posts visible on profile
Pre-Launch Week -1 |  | Launch | Seed content (Post 3 of 4) | Carousel: Uche's transformation story (strongest testimonial) | 15-30s Uche before/after clip | Still silent. | 3 posts visible = credible profile
Pre-Launch Week -1 |  | Launch | Seed content (Post 4 of 4) | Carousel: "How it works" — Join → Pick your path → Show up → See progress | 30s explainer: "How to join SwimBuddz in 60 seconds" | Still silent. Profile now has 4 posts. | Profile looks established
LAUNCH Week 0 |  | Launch | Announce on WhatsApp + all channels | Post a "We're officially on Instagram" announcement reel | Post a "We're on TikTok" announcement | 1. WhatsApp group: "We're live! Follow + like + comment on the first post" 2. Every coach shares to personal account 3. Ask 10-15 members to follow and engage in first hour 4. Pin announcement in WhatsApp group | 50-100 followers day 1 20+ comments on first post
LAUNCH Week 0 |  | Launch | First 48 hours: engage aggressively | Reply to EVERY comment. Reply with questions to keep threads alive. Like every follower's recent post. | Same. Reply to all comments. Follow back relevant accounts. | Check notifications every 2 hours for first 48 hours. This is the most important engagement window for the algorithm. | Signal to algorithm: this account is active and engaging
Post-Launch Week 1 |  | Founding Members | Start "Meet the Founding Members" series | Carousel: Member spotlight #1 — one of the most active/recognizable members | 15s: "Meet [Name] — founding member of SwimBuddz" | DM the featured member: "You're our first feature! Share to your story and tag us." Their reshare = 200-500 new eyeballs. | Member reshare reach
Post-Launch Week 2 |  | Community Vibes | Session day content (pool + post-swim hangout) | Photo dump: Best session moments + eating together after | POV: "Your first SwimBuddz Saturday" montage | Content Buddy captures. Share to WhatsApp group. Cross-post Story. | Saves & shares
Post-Launch Week 3 |  | Founding Members | "Meet the Founding Members" #2 | Carousel: Member spotlight #2 — different demographic/tier if possible | 15s: Member intro clip | Same DM-and-reshare playbook. Tag the member. | Growing follower base through member networks
Post-Launch Week 4 |  | Milestone Showcase | First milestone/transformation post | Reel or carousel: Academy student journey | Emotional journey compilation (30-60s) | Tag the student. DM to reshare. Share in WhatsApp group. This is the post designed to go semi-viral. | First breakout post potential

## 3-Month Calendar
Week | Date | Pillar | Instagram Format | Instagram Caption | TikTok Format | TikTok Caption/Hook | Content Source | Distribution Plan | Status
1 | May 11, 2026 | Founding Members | Carousel: Member Spotlight #3 | "💡 Meet [Name] — one of the founding members of SwimBuddz. [3-4 facts from their spotlight] This is what community looks like. #SwimBuddz #FoundingMembers #SwimCommunity | 15s member intro on camera | "Meet [Name] from SwimBuddz" [member shares why they swim] | Member Spotlight from WhatsApp | DM member to reshare. Tag them. | 📋 Planned
2 | May 18, 2026 | Community Vibes | Reel: Full Saturday experience (pool + food + vibes) | "Pool. Food. Friends. Repeat. 🌊 This is what Saturdays look like at SwimBuddz — the swim is just the beginning. #SwimBuddz #SaturdaySwim #LagosLife | POV: Full SwimBuddz Saturday (pool → eating together) | "POV: SwimBuddz Saturdays hit different" [pool + hangout clips] | Content Buddy session + hangout photos | Share to Story. Post in WhatsApp. Coaches reshare. | 📋 Planned
3 | May 25, 2026 | WhatsApp Repurpose | Carousel: Question of the Week + best answers | "Every Thursday, we ask our swimmers a question. This week: 💬 "[Question]" Swipe for their answers → #SwimBuddz #AskASwimmer #SwimCommunity | Coach answers QOTW on camera (30s) | "We asked our swimmers: [question]" [coach gives expert answer] | Thursday QOTW from WhatsApp | Tag members whose answers are featured. | 📋 Planned
4 | Jun 01, 2026 | Social Proof | Testimonial + WhatsApp screenshots carousel | "What the group chat looks like after a SwimBuddz session 💬 We don't need to tell you it's good. Our members already did. #SwimBuddz #RealReviews #SwimCommunity | Member answers 'why I keep coming back' (15s) | "Why do you keep coming back to SwimBuddz?" [member responds] | WhatsApp screenshots (blur numbers) + testimonial | Share to Story. DM featured member. | 📋 Planned
5 | Jun 08, 2026 | Milestone Showcase | Reel: Academy journey compilation (strongest student story) | "From [fear] to [achievement] 🥹 This is [Name]'s SwimBuddz Academy journey. Every milestone, every breakthrough. Your story could be next. #SwimBuddz #SwimAcademy #LearnToSwim | Full journey compilation with emotional audio (30-60s) | "[He/She] was TERRIFIED on Day 1..." [journey compilation] | Academy milestone video uploads | Tag student. DM to reshare. WhatsApp group. Coaches reshare. THIS is your breakout post. | 📋 Planned
6 | Jun 15, 2026 | Founding Members | Carousel: Member Spotlight #4 — different tier/demographic | "💡 Meet [Name] [Their story] #SwimBuddz #FoundingMembers #MemberSpotlight | 15s member intro clip | "Meet [Name] — founding member of SwimBuddz" | WhatsApp Member Spotlight | DM member to reshare. | 📋 Planned
7 | Jun 22, 2026 | Education | Carousel: "3 things beginners get wrong" (5 slides) | "Stop doing this if you're learning to swim 🚫 1. Holding your breath instead of exhaling 2. Lifting your head too high 3. Kicking from the knees Swipe for fixes → #SwimBuddz #SwimTips #LearnToSwim | Coach explains one thing in <30s | "The #1 mistake every beginner makes..." [coach at pool] | Coach films at pool (Brief A) | Save-worthy content. Ask followers to save + share. | 📋 Planned
8 | Jun 29, 2026 | Community Vibes | Photo dump: Best moments of the month (pool + hangout + candids) | "The pod 🐬 SwimBuddz isn't just swimming. It's the crew at the pool, the food after, the group chat at midnight. #SwimBuddz #SwimSquad #LagosWeekend | Group energy montage with Afrobeats | "Find your people at the pool (and at lunch)" [montage] | Gallery + Content Buddy + hangout photos | Tag everyone visible (with consent). They reshare. | 📋 Planned
9 | Jul 06, 2026 | Transformation | Carousel: Side-by-side technique + stat card reveal | "Week 1 vs Week 8 🔥 Same swimmer. Same pool. Different stroke. Last slide: their stats — 10 pool hours, Top 6%. #SwimBuddz #ProgressNotPerfection #SwimAcademy | Split-screen: Day 1 vs graduation + stat card | "Same person. 8 weeks apart." [split screen → stat card] | Academy before/after + quarterly stat cards | Tag student. Encourage stat card sharing with #MySwimBuddzStats | 📋 Planned
10 | Jul 13, 2026 | WhatsApp Repurpose | Carousel: Best of QOTW — monthly compilation | "💬 Best of Question of the Week Our swimmers' best answers this month → Join the conversation: link in bio. #SwimBuddz #AskASwimmer #SwimCommunity | Coach rapid-fires 3 questions in 30s | "3 questions from our swimmers — answered in 30 seconds" | QOTW archives from WhatsApp | Tag featured members. Cross-post to Story. | 📋 Planned
11 | Jul 20, 2026 | Founding Members | Carousel: Member Spotlight #5 | "💡 Meet [Name] [Story] #SwimBuddz #FoundingMembers #SwimCommunity | 15s member intro | "Meet [Name]" | WhatsApp Member Spotlight | DM to reshare. | 📋 Planned
12 | Jul 27, 2026 | Milestone Showcase | "SwimBuddz Q[X] Wrapped" stat card carousel (8-10 slides) | "🏊 SwimBuddz Wrapped [X] pool hours [X] swimmers at 100% attendance [X] Academy graduates Swipe to see Top Swimmers → Share YOUR card: #MySwimBuddzStats #SwimBuddz #Wrapped #SwimLagos | Stat cards flashing + pool highlights montage | "Our swimmers logged [X] HOURS 🔥" [stat cards + montage] | Quarterly report stat cards from platform | DM EVERY featured member: "Share your card to your story!" This is your highest-reach post of the quarter. | 📋 Planned

## Pillars & Strategy
Pillar | Goal | Target Audience | Best IG Format | Best TT Format | Content Source | Distribution Play | KPI
Transformation | Drive Academy sign-ups | Non-swimmers, parents | Carousel (before/after) | 15-30s progress clip | Academy milestones | Tag student → reshare | Profile visits → site clicks
Community Vibes | Build FOMO, drive sign-ups | Social crowd, fitness-curious | Reel / photo dump (pool + hangout) | POV / montage | Session albums + hangout photos | Tag members → reshare | Saves & shares
Education | Build trust & authority | Beginners, curious adults | Carousel (swim tips) | Coach to camera <30s | Coaches + QOTW | Save-worthy → bookmarks | Saves
Social Proof | Convert warm leads | Anyone considering joining | Testimonial + WA screenshots | Member on camera | Testimonials + WA reactions | DM featured member | DMs about sign-ups
WhatsApp Repurpose | Show community depth | Lurking followers | Carousel (QOTW / Spotlight) | Coach answers / member intro | QOTW + Member Spotlight | Tag featured members | Comments & follows
Milestone Showcase | Celebrate + recruit | Parents, Academy prospects | Reel (journey) / stat cards | Emotional compilation | Milestone videos + stat cards | DM ALL featured → reshare storm | Shares + DMs + reshares
Founding Members | Build origin story + reach | Member networks (200-500 each) | Carousel (member spotlight) | 15s member intro | WhatsApp spotlight + photos | DM member → story reshare | Follower growth via networks

## Hashtags
Category | Hashtags
Brand (always use) | #SwimBuddz
Academy | #LearnToSwim #SwimAcademy #AdultSwimmer #NeverTooLate #KidsSwimming
Club | #SwimFitness #SwimTraining #SwimLife #LapSwimming
Community | #SwimSquad #SwimCommunity #NigeriaSwims
Location | #SwimLagos #LagosLife #LagosWeekend #ThingsToDoInLagos
Motivation | #ProgressNotPerfection #FearToConfidence #Consistency #ShowUp
General Swim | #SwimTips #SwimmerLife #PoolDay #SwimmerStories
WhatsApp Content | #AskASwimmer #MemberSpotlight
Quarterly Wrapped | #MySwimBuddzStats #Q1Wrapped #SwimStats
Founding Members | #FoundingMembers #SwimBuddzOGs

## Content Sources
Source | Where It Lives | How To Collect | Pillar It Feeds | Frequency
Academy milestone videos | Student uploads on platform | Pull from Academy milestone evidence in admin dashboard | Transformation, Milestone Showcase | Per cohort
Quarterly report stat cards | Platform reporting_service | Screenshot/export from member dashboards | Milestone Showcase, Social Proof | Quarterly
Session/event photos | Gallery + Content Buddy | Content Buddy drops in WA group; pull from gallery | Community Vibes | Weekly
Post-swim hangout photos | Members' phones | Content Buddy captures; members share to WA | Community Vibes | Weekly
WhatsApp group reactions | SwimBuddz WhatsApp | Screenshot best messages (blur numbers) | Social Proof | After each session
Question of the Week | WhatsApp (Thursdays) | Screenshot question + top 3-5 answers | WhatsApp Repurpose, Education | Weekly
Member Spotlight | WhatsApp (weekly rotation) | Ask permission; screenshot or rewrite | WhatsApp Repurpose, Founding Members | Weekly
Written testimonials | swimbuddz.com | Already on site; use as caption copy | Social Proof, Transformation | Existing
Video testimonials | Need to film | Use filming Brief D; film at pool | Social Proof | One-time then ongoing
Coach tip videos | Coaches film at pool | Use filming Brief A | Education | As needed
Journey compilations | Compiled from milestones | Edit together all milestone clips per student | Milestone Showcase | Per cohort graduation

## Weekly Metrics
Week Ending | Platform | Post | Reach | Likes | Comments | Saves | Shares | Profile Visits | Website Clicks | DMs (Sign-up Interest) | New Followers | Member Reshares | Notes
May 18
May 25
Jun 01
Jun 08
Jun 15
Jun 22
Jun 29
Jul 06
Jul 13
Jul 20
Jul 27
Aug 03

## Repurposing Chain
Core Asset | TikTok | IG Reel | IG Carousel | IG Story | WhatsApp
Academy Journey Video (60s milestone compilation) | 30s cut with trending audio. Hook: "She was TERRIFIED..." | Same or slightly longer cut | Screenshot key moments as stills with text overlays per slide | BTS: "We just edited [Name]'s reel and we're emotional" | Full uncut version in group
Quarterly Stat Cards | Fast montage of cards flashing with upbeat audio | Same montage or slideshow | "SwimBuddz Q1 Wrapped" — community stats + top cards | Individual cards tagging each member. "Share to your story!" | Post everyone's cards. Members screenshot theirs.
Question of the Week | Coach answers on camera in 30s | Same video | Slide 1 = question, Slides 2-5 = member answers | Poll: "What's YOUR answer?" with 2 options | Share IG post back: "Your answers made it to Instagram!"
Member Spotlight (from WhatsApp) | 15s member intro on camera | Same video or photo slideshow | Photo + name + key facts + why they swim + fun fact | "Meet this week's featured swimmer!" with link to post | "[Name] is featured on our IG today! Go show love!"
Coach Tip Video (30s poolside) | Native TikTok with trending audio | Same video | Tip broken into 3-4 carousel slides with illustrations | "New swim tip! Swipe up to see the full post" | Share in group: "New tip from Coach [Name]"
Post-Swim Hangout (photos + clips) | POV montage: pool → food → vibes | Same montage | Photo dump: 8-10 best moments from session + food | Quick candid clip with "This is why we show up" | Drop raw photos in Content WA group
Video Testimonial (30s member clip) | Native TikTok with caption overlays | Same video | Quote graphic (slide 1) + video (slide 2) + CTA (slide 3) | Share with "This is why we do this" | Full clip in community group